## Overall Project Plan
# | Tasks | . | Stake Holder | Status | ETA | Comments
1 | Sprint 2 Testing
1.1 | Sprint 2 Testing - Internal QA + BONDs |  | QA
1.1.1 | Bugs reported | -161 Open Issues (64 Important issues) status of 5-may -21 issues with Fix_Sprint3 tag in open state -Fix_Sprint3 tag to be removed - Attire Filter bug to be taken up -How to move forward with the AI related bugs | Dev | In Progress
1.1.1a | Blocker/ Critical Being done by Dev being tested by Internal QA | DAM Preprod is being used for testing |  | In Progress
1.1.3 | issues/bugs to be shifted to sprint 3 - 105 bugs/ enhancements (comparison with existing DAMs) | sprint3 tag is attached to those bugs | QA | Completed
1.1.4 | Will use Dev environment for Demo only, no SIT environment | Dev does development on local; during testing, deployment will not be on Dev |  | Completed
1.2 | Image tagging prerequisites |  | Rijul | Completed | 2023-03-17
1.2.1 | 10 bonds to be onboarded for image tagging training |  | Angad | Completed | 2023-03-15
1.2.2 | GetIT - installation of Python on Company laptops | For all 10 onboarded bonds | GeT IT (Sarvesh Tandil) | Completed | 2023-03-16
1.2.3 | Create SOP for Image downloading(Web Scraping) and image labeling |  | Rijul | Completed | 2023-03-15
1.2.4 | Create a group and share documents with the Bonds |  | Rijul | Completed | 2023-03-15
1.2.5 | Arrange KT for Web Scraping and labeling |  | Pritam / Nitin | Completed | 2023-03-16
1.2.6 | Assign Person Tags to each Bond |  | Rijul | Completed | 2023-03-16
1.2.7 | Create tags folder for each tag on sharepoint |  | Rijul | Completed | 2023-03-17
1.3 | Image downloading and tagging | 22 tags and 11 persons, approx. 1000 images per tag | Rijul | Completed | 2023-03-23
1.3.1 | 1000 Image downloads for each tag using scraping or manually |  | Bonds | Completed | 2023-03-23
1.3.2 | Deleting unwanted and irrelevant images | The final count shall be 1000 | Bonds | Completed | 2023-03-23
1.3.3 | Labeling each image | KT for Multi labeling Multi labeling each image - Chek final tag list | Bonds | Completed | 2023-03-23
1.3.4 | Reviewing Image |  | Bonds | Completed | 2023-03-23
1.3.5 | Uploading image on share point or S3 bucket | https://rilcloud.sharepoint.com/:f:/s/GroundWorkTeam/EqBK1JT6Q-lLtd_Ed8OUVmoB3rjWW959grGbs_n3Ee_b4Q?e=Gdnylm | Bonds/Pritam | Completed | 2023-03-23
1.4 | Building Model using Labelled Data - 1st Set | 50 tags have been trained so far | AI team | Completed
1.4.1 | Bench marking Report to be shared |  | Pritam | Completed | 2023-03-22
1.4.2 | Labelling Completion |  | Rijul | Completed
1.4.3 | Data Augmentation | Multyplying imgaes 4x for training the model | Pritam | Completed | 2023-03-24
1.4.4 | Incomplete tags to be augmented |  | Rijul | Completed | 2023-03-24
1.4.5 | Model Training - estimate of services needed to be shared | Akash is coordinating with Pritam | Pritam | Completed
1.4.6 | Model training- 3 types of sets | Approach to be discussed (AWS requirement to be communicated to KK sir) Test set, Train set, Validation set(tbc) | Pritam | Completed | 2023-03-27
1.4.8 | Model Dev testing |  | Pritam | Completed
1.4.9 | Issue Resolution | AI tags issue resolution | Pritam | In Progress
1.5 | Model Testing on DAM application | Testing TBD by AI team and QA team | QA + Bond | Completed
1.5.1 | User testing on DAM |  | QA + Bond | Completed
1.6 | Model training - 2nd set |  | Rijul/ AI team | In Progress | 2023-04-03
1.6.1 | Onboarding 25 more BOND testers | Total 22 Bonds are onboarded(10 earlier, 12 New) | Angad | Completed
1.6.2 | KT to be arranged for BOND testers |  | Rijul | Completed
1.6.3 | Labelling to be completed - downloaded, reviewed |  | Rijul | completed | 2023-03-31
1.6.4 | Data Augmentation | Data augmentation for 77 tags | Pritam | In Progress | 2023-04-12
1.6.5 | DevOps requirements for Model training to be communicated | Aakash communicating with AI team | Pritam | Completed
1.6.6 | Model testing to start |  | Pritam | Not Started
1.6.7 | Model training to complete |  | Pritam | Not Started
1.7 | Model Testing for 2nd set set |  | QA + Bond | Not Started
1.8 | Demo with Prashant & Vasudha | AT 3PM Tomorrow(12-apr) Increase instance size during Demo - Aakash Cleanup the DAM website - QA Determine the working functionalities to focus on. |  | Completed | 2023-04-05
1.8.1 | PPT deck to be prepared of - what we have done - What value will be added for Bluekraft - time saving, reducing people, reducing manual work, quality of works, what is coming (video search) | https://rilcloud.sharepoint.com/:x:/r/sites/GroundWorkTeam/Shared%20Documents/Campaigns/DAM/User%20Stories%20%26%20PRDs/Feature%20Comparision%20List%20V1.1.xlsx?d=w101ab044bf1b428da77dad0ed7761321&csf=1&web=1&e=EChGXs | Ritul | Completed
1.8.2 | Enhancements based on Demo Inputs | Should we take this in sprint 3 or 4? | Product Team | In Progress
a | Media uploader title to be replaced with Photographer related Terminology | To be dicussed and confirmed |  |  |  | Have explained this to BK team, title can be as it is for now, can be re-confrimed post S2 UAT feedback
b | Media Validator name to be replaced | To be dicussed and confirmed |  |  |  | Have explained this to BK team, title can be as it is for now, can be re-confrimed post S2 UAT feedback
c | Enhancement in Search logic |  |  |  |  | Will be part of S3
d | Two filter options in search result one for "AND" Result one for other related search results | Product team will create a flow for this |  |  |  | Will be part of S3 - Exact Match/Partial Match
e | Free style Pencil Cropping | Requirement to be dicussed and confirmed in detial with BK team |  |  |  | Will be part of S4
f | Share link for the users who don't have DAM access |  |  |  |  | Will be part of S3 - Custom Links
1.9 | Search logic to be discussed after integrating AI tags | Confirm the flow with product, AI and Dev team |  |  | 2023-03-31
2 | Sprint 3 User Story, Wireframes & Flow creation
2.1 | Sprint 3 scope finalization |  | Product | In Progress | 2023-03-24
2.1.1 | Sprint 3 walkthrough |  | Product | Completed | 2023-04-04
2.2 | User stories and wireframes |  | Product | Completed | 2023-03-24
2.3 | UI + UX - Figma |  | Hiren | Completed | 2023-04-11
2.4 | HTML & CSS | 3 more bonds are working on HTML/CSS 8 features- 26 screens | Hiren | Completed | 2023-04-14
2.4.1 | Share the code on SharePoint |  |  | Completed
2.5 | Bluekraft dependencies |  | Bluekraft
2.6.1 | New Tags confirmation with BlueKraft
2.6.2 | Video formats - mp4 & mov | Can be downloaded from YouTube. Does AI team need help with this?
2.6.3 | Confirmation about the type of videos which needs to be downloaded
2.6.4 | Image formats to be confirmed | RAW images are documents in our DAM
3 | Sprint 3 Development
3.1 | Devops Optimization | Instance optimization to be taken up
3.1.1 | Instance size reduction on Dev & Staging - t2.2xlarge to t2.small
3.1.2 | Stopped instances to be deleted
3.1.3 | Moving infra from Tokyo to Mumbai
3.1.3.a | AI ML which services are available in Tokyo
3.1.4 | Reserved instances instead of On-demand | 3 years & 1 years are options; timeperiod might be dependent on instance
3.2 | User Stories | 30 User stories - 24 in active state
3.3 | Sprint 3 Dev Start | Product team coordinating with the dev for the development
3.3 | Discussion On AI clustering
Flows created
3.4 | SFTP sevices to be decided |  | Aakash | Completed
3.4.1 | Instance creation
3.5 | WhatsApp Business, Facebook Business Manager, Google API Access
4 | DevOps Merging
4.1 | Provide Bond DevOps Access |  |  | Completed
4.2 | User Stories to be shifted to Bond Projects |  |  | Not Started

## Image AI Tags Plan
# | Work item | Comment | Stake Holder | ETA
1 | Discussion on tags |  |  | 14/03/23
1.1 | Consolidation required in tags | What to do when there is overlap in tags? For example | Pritam/Rijul
1.2 | Synonyms & Child tags - Manual mapping - list of synonyms are configured in module AI does this synonym & child mapping | Idea: Consider synonyms to be part of user search To be reviewed by pritam | Pritam/Rijul
1.3 | Image formats | svg, png, jpeg, tiff, jpg, jfif, webp currently used by
1.4 | Tags to be reviewed with Bluekraft | Image formats to be confirmed
2 | Labelled data of Person, Gesture, Emotion & Attire to be prepared | tag_asset_count_01032023.xlsx
2.1 | Persons - 1000 images of person to be made available | How should Bonds do this? Each bond to do 1000 images
i | Training - 1 week long; in War Room; 1 of each type of tag
ii | Downloading images
Check UAT of existing DAM for images
Web scraping tool - not-so-high quality images
Preference for high-quality images - labelled images from existing DAM/ PIB press information bureau
iii | Cleaning also needed; delete unneeded data
iv | Labelling images - downloading imaging software
v | Labelling review - labels to be reviewed; | labels to be exact
vi | Access for Bonds | upload to shared Sharepoint site
2.2 | Emotions - Workshop by AI team on how to do labelling

## WBS S3
# | Feature | Details | Wireframes status | Figma status | HTML/CSS status | Dev Status | AI Dependency | User story link | Start Date | End Date | Comment
1 | Large File Upload/Download - SFTP | As a User I want to Upload/Download a file larger than 800 Mb. | TBD | TBD | TBD |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/330 |  |  | DEV Comment- User story needs to be defined properly and Wireframes and Figmas to be defined RND to be done by product team
2 | Upload Status | As a validator, I should be able to view progress of the uploads while Uploading the Assets | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/331
3 | Video Transcriptions | Transcript Generation | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/354
4 |  | As a Retriever, I should be able to view the transcripts in a side panel when the video is played along with the timestamps | [5 empty] | https://devops.jio.com/TRS/DAM/_workitems/edit/355
5 | Search to include Video transcription |  | Completed | Completed | Completed | [5 empty] | User story not defined- What will be the priority of the video transcriptions in the search result | video transcript search will be last prioriity dev been informed or can be searched through advance filter as shown in figma
6 | Static filters below seach bar | As a Retriever, I want to view asset type filter below the search bar | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/332
7 | Advance filter | As a Retriever I want to view the Advance filter section with two sections: 1. Search “folder search” 2.Search within option – ( The retriever could search only from tags if he/she selects… search within “tag”) Search within option will be for Description, AI- Manual Tag s, Event, Location, Title, Video Transcript | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/333
8 | Asset Details (Below Thumbnail) | As a Validator/admin I want to view the asset details below the assets | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/334 |  |  | Need Confirmation From Product Team- 1-Upload Date is not present on the Figmas as mentioned in the User story 2-Tagged/Untagged upload is mentioned in the journey but it is merged in the Figma | Update date present
9 | Select icon on the Asset thumbnail | As a Retriever I want to view the select icon checkbox over the Asset thumbnail | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/335
10 | Image Preview | As a Validator/Admin/Retriever I want to view image in the full screen | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/336
11 | Trim Video/Audio Assets |  | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/338
12 | Add to Collections |  | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/339 |  |  | 1)The below line is mentioned in the user story, Need confirmation for this "The Retriever can also view the “Add to collection” option below the Trim/Crop button once he clicks on the asset and lands on a different page." 2)Remove(from collection) button is not present in the Figma instead add to collection button is present which is irrelevant | Delete button is present will remove the add to collection
13 | Tagging Status | As a Validator, I want to view the tagging status button on the Tag asset form | To be confirmed |  |  |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/340 |  |  | Figam of radio button in tag asset form is absent (Refering to user story)
14 |  | As a Media Validator , I want to view the tagging status of the assets and folders | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/341 |  |  | User story point 9 to be discussed | As discussed the transcript will not be generated instantly , it will be generated by a scheduler.
15 | Filters in tables- Role configuration,User management,Tag, Event & Folder management | [6 empty] | https://devops.jio.com/TRS/DAM/_workitems/edit/337 |  |  | Already present in DAM. User story in active state Confirm if any chages are required based on the user story. If no then close the user story
16 | G-Drive Integration( Share) | As a Retriever, I want to share the asset via Google drive | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/345 |  |  | Is it possible to Save/share multiple assets in the G drive acCount at once? | Yes multiple share is possible
17 | Session Timeout | As a User, I should be warned of session expiry 60 sec. prior, if the webpage remains inactive for 45 mins | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/342 |  |  | what kind of unsaved data will be lost is not defined in the user story
18 | Notification Icon | As a Validator , I want to view notification icon at the top menu bar | [5 empty] | https://devops.jio.com/TRS/DAM/_workitems/edit/356
19 | Reassign event | As an Admin I want to view the Reassign event through Event Management | Not Required | Not Required | Not Required | Completed |  | https://devops.jio.com/TRS/DAM/_workitems/edit/343 |  |  | Wireframes and Figma missing
20 | Reset Password | As a user I must receive "Reset Password" link via email | [5 empty] | https://devops.jio.com/TRS/DAM/_workitems/edit/344
21 | Clip List | As a Retriever , I want to view the clipped list section in the menu bar | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/346 |  |  | Role of the clip list icon present on the thumbnail is not defined in the user story User story and Figma to be updated | User story is present and it highlihghts "The Clip list menu will be highlighted in the menu bar as an icon."
22 | Saving Trim/Cropped assets | As a Validator I want to edit the assets and save the trimmed/cropped assets in the same folder as the original asset | [5 empty] | https://devops.jio.com/TRS/DAM/_workitems/edit/349
23 | Validaor tab options | As a Validator I want to view options in tab section of the Validator's page | [5 empty] | https://devops.jio.com/TRS/DAM/_workitems/edit/351 |  |  | Role of "Clear selection" button is not defined in user story What all features can be used on multiple select to be defined in the user story | Multiple selection is not provided to validator section only retriever has this
24 | Icons over asset Thumbnail | As a Media Validator I want to view icons over the asset thumbnail | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/352
25 | Tab options | As a Retriever, I want to view options in tab section of the Retriever's page - Share Download Add to Collection select all | Completed | Completed | Completed |  |  | https://devops.jio.com/TRS/DAM/_workitems/edit/353
26 | Create Directory at entry level | As a Media Validator/Uploader I want to create a new directory at every level | [5 empty] | https://devops.jio.com/TRS/DAM/_workitems/edit/359
19 | Redesign Menu Bar: Combine Media Uploader and Validator in one Module called 'Assets' |  | Pending | Pending | [6 empty] | Need to convey the flow Wirerame ready
20 | Image AI tagging - Feedback loop |  | Pending | Pending | [6 empty] | S4
21 | Search History store (Collections Revamp) |  | Pending | Pending | [6 empty] | S4
22 | AI Tagging of Video frames |  | Pending | Pending | [6 empty] | S5
23 | Use of the short cut keys |  | Pending | Pending | [6 empty] | S4
25 | Dashboard Reports |  | Not available | Not available | [6 empty] | S4
26 | Folder Management Redesign |  | Pending | Pending | [6 empty] | S4
16 | Role Config |  | Completed | TBD | [6 empty] | Need discussion with Dev & BK team

## Links
Name | Links
Asset Lifecycle Management | Asset Lifecycle Management.pptx
System Setup | System Setup.pptx
User Lifecycle Management | User Lifecycle Management.pptx
User Stories | Sprint 1 User Stories V1.3.xlsx
DevOps board | https://devops.jio.com/TRS/DAM/_boards/board/t/DAM%20Team/Features
Feature mapping
Old DAM Site | https://newdam-stage.nmarchive.in/dashboardnew | nitin.rathi@opalina.in DamUat | subodhrajpoot1992@gmail.com 12345
Testing Site | http://dev.tagsmarter.com/dashboard/dash-home | admin@gmail.com Admin@123
Figma | https://www.figma.com/file/a7SgzHpM59j2PGPtkx7mj8/NM-DAM?node-id=33%3A10298&t=F9zdLLVoSlfBYiiN-1
Admin | https://www.figma.com/proto/chIEJPVt4g7eFSbFe9LtOh/NM-DAM?page-id=82%3A663&node-id=1308%3A61922&viewport=1589%2C2580%2C0.05&scaling=scale-down&starting-point-node-id=1308%3A61922
Validator | https://www.figma.com/proto/chIEJPVt4g7eFSbFe9LtOh/NM-DAM?page-id=3854%3A88123&node-id=3854%3A93021&viewport=704%2C676%2C0.07&scaling=scale-down&starting-point-node-id=3854%3A93021
Retriever | https://www.figma.com/proto/chIEJPVt4g7eFSbFe9LtOh/NM-DAM?page-id=82%3A662&node-id=574%3A28761&viewport=1713%2C1447%2C0.07&scaling=scale-down&starting-point-node-id=574%3A28761

## AI-Tags_Sprint4
Sr. No | Emotions | Gesture | Gesture_OD Link | Attire | Attire_OD Link | Person | Person Link
27 | Fear | waving hands | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?prefix=images/team_members/ankit/&region=ap-south-1 | Turban | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/batches/Attire/Turban/&showversions=false https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/jatin/gestures/&showversions=false | Akshay Kumar | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
24 | Neutral | namaskar |  | Shirt | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/jatin/gestures/&showversions=false | Amit Shah | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/ |  | fruits.zip | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/jatin/&showversions=false
28 | Angry | folded hands | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/jatin/gestures/&showversions=false | Modi Jacket | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/batches/batch1/&showversions=false https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?prefix=images/batches/Reviewed_Labels/&region=ap-south-1 | Anthony Albanese | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
29 | Sad | handshake | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?prefix=images/batches/Gesture/HandShake/&region=ap-south-1 | Kurta | l | Antonio Costa | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
30 | Happy | presenting cheque | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/jatin/gestures/&showversions=false | Scarf | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/mohit/pre_labelled/&showversions=false | Anurag Thakur | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
31 |  |  |  | Beard | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/mohit/pre_labelled/&showversions=false | Arun Jaitley | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
32 |  |  |  | Glasses | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/mohit/pre_labelled/&showversions=false | Arvind Kejriwal | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
33 |  | Salute | S3 ¦ Global (amazon.com) | Shoes | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/batches/batch1/&showversions=false https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?prefix=images/batches/Reviewed_Labels/&region=ap-south-1 | B D Mishra | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
34 |  | lighting lamp | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/jatin/gestures/&showversions=false | Coat | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/batches/batch1/&showversions=false https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?prefix=images/batches/Reviewed_Labels/&region=ap-south-1 | Barack Obama | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
22 |  |  |  | Cap | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/jatin/gestures/&showversions=false | Benjamin Netanyahu | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/ | class lable file with label id?
35 |  |  |  | Saree | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=images/team_members/jatin/gestures/&showversions=false | Bhagwant mann | ShareIt
36 | [5 empty] | Bhupendrabhai Patel | ShareIt
37 | [5 empty] | Biswabhusan Harichandan | ShareIt
38 | [5 empty] | Borris Johnson | ShareIt
39 | [5 empty] | conrad sangma | ShareIt
40 | [5 empty] | Devendra Fadnavis | ShareIt
4 | [5 empty] | Donald Trump | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
21 | [5 empty] | Droupadi Murmu | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
41 | [5 empty] | Eknath Shinde | ShareIt
42 | [5 empty] | Emmanuel Macron | ShareIt
43 | [5 empty] | Fumio Kishida | ShareIt
44 | [5 empty] | Gurinder Singh Dhillon | ShareIt
45 | [5 empty] | Gurmit Singh | ShareIt
46 | [5 empty] | Hema Malini | ShareIt
47 | [5 empty] | Hemant Soren | ShareIt
26 | [5 empty] | Himanta Biswa Sarma | ShareIt
23 | [5 empty] | Jagat Prakash Nadda | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
5 | [5 empty] | Joe Biden | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
48 | [5 empty] | Justin Trudeau
49 | [5 empty] | Kamala Harris
50 | [5 empty] | L.K. Advani
51 | [5 empty] | mamta banerjee
52 | [5 empty] | Manik Saha
53 | [5 empty] | Manish Sisodia
54 | [5 empty] | Manmohan Singh
55 | [5 empty] | Manohar Lal Khattar
56 | [5 empty] | Manohar Parrikar
57 | [5 empty] | Manoj Tiwari
58 | [5 empty] | Mayawati
59 | [5 empty] | Melania Trump
60 | [5 empty] | Mohammed bin Salman Al Saud |  |  |  |  | Sheikh Mohammed bin Zayed Al Nahyan
61 | [5 empty] | Mukesh Ambani
62 | [5 empty] | Mulayam Singh Yadav
63 | [5 empty] | N. Biren Singh
64 | [5 empty] | Neeraj Chopra
65 | [5 empty] | Neiphiu Rio
9 | [5 empty] | Nirmala Sitharaman | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
66 | [5 empty] | Nita Ambani
67 | [5 empty] | Nitin Gadkari
68 | [5 empty] | Nitish Kumar
69 | [5 empty] | Olaf Scholz
70 | [5 empty] | P. S. Sreedharan Pillai
71 | [5 empty] | P.Chidambaram
72 | [5 empty] | Parmod Sawant | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
73 | [5 empty] | Piyush Goyal
74 | [5 empty] | PK Mishra
75 | [5 empty] | Pratibha Patil | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
14 | [5 empty] | PV Sindhu | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
76 | [5 empty] | Radha Mohan singh | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
77 | [5 empty] | Raghubar Das | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
78 | [5 empty] | Rahul Ghandhi | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
8 | [5 empty] | Rajnath Singh | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
7 | [5 empty] | Ram Naik | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
10 | [5 empty] | Ram Nath Kovind | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
79 | [5 empty] | Ramdas Atvale | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
13 | [5 empty] | Ratan Tata | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
15 | [5 empty] | Ravi Shankar Prasad | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
80 | [5 empty] | Recep Tayyip Erdogan | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
81 | [5 empty] | Reuven Rivlin | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
82 | [5 empty] | S Jaishankar | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
83 | [5 empty] | Sachin Tendulkar | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
16 | [5 empty] | Sharad Pawar | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
84 | [5 empty] | Sheikh Mohammed bin Zayed Al Nahyan | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
17 | [5 empty] | shinzo abe | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
6 | [5 empty] | Shivraj Singh Chouhan | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
85 | [5 empty] | Smriti Irani | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
12 | [5 empty] | Sonia Gandhi | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
86 | [5 empty] | Sushil Modi | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
87 | [5 empty] | Sushma Swaraj | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
88 | [5 empty] | Tejasvi Surya | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
89 | [5 empty] | Thawar Chand Gehlot | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
25 | [5 empty] | Uddhav Thackeray | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
90 | [5 empty] | Uma Bharti | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
91 | [5 empty] | Ursula Von Der Leyen | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
92 | [5 empty] | Venkaiah Naidu | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
93 | [5 empty] | Vicky Kaushal | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
3 | [5 empty] | Vijay Rupani | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
11 | [5 empty] | Vladimir Putin | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
94 | [5 empty] | willem-alexander | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
2 | [5 empty] | Xi Jinping | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
95 | [5 empty] | Yogendra Yadav | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
1 | [5 empty] | Yogi Adityanath | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
20 | [5 empty] | Yoshihide Suga | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
19 | [5 empty] | Yoweri K. Museveni | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/
18 | [5 empty] | YS Jagan Mohan Reddy | https://s3.console.aws.amazon.com/s3/buckets/aimldevbucket-1?region=ap-south-1&prefix=dataset/images/person/

## AWS login ids and passwords
User name | Password | Console login link | aws configure
Pritam.Patra@ril.com | 8hX6+]$dkOcVQ&p | https://579654570707.signin.aws.amazon.com/console | User name | Access key ID | Secret access key | Region name | Default output format
Nitin.Bhore@ril.com | ($Mp_yeYe])-{IW | https://579654570707.signin.aws.amazon.com/console | DAMAPP | AKIAYN5Q22LJ6SD6BZXN | JcdIzdGK4QEqTOVZK9tmzKxdjDywJexHMXZ/GOdU | ap-northeast-1 | JSON
Archana.Kavya@ril.com | fS'q*uB2OXk(Uq5 | https://579654570707.signin.aws.amazon.com/console
Abhilash.Nair@ril.com | LlVs&Ysk¦H&Si[7 | https://579654570707.signin.aws.amazon.com/console
Bhuvaneshwari.S@ril.com | 7ao2^8!oVAVA&t0 | https://579654570707.signin.aws.amazon.com/console | Jump Server Details:
Mohammad.Danish@ril.com | o*('V_gCe2GA21V | https://579654570707.signin.aws.amazon.com/console | Jumpserver id: 3.111.32.29 password:-744VkkUE User Name: damuser
Umesh.Satpute@ril.com | UVM]D9siU+nTxH1 | https://579654570707.signin.aws.amazon.com/console
Sachin.Dwiwedi@ril.com | i@Q[Y_d73dvU)46 | https://579654570707.signin.aws.amazon.com/console
Mohit.Jain@ril.com | Q'(F%}4v'dn#(VF | https://579654570707.signin.aws.amazon.com/console
Ankit.Singh@ril.com | G$3iWmQuR2eX49A | https://579654570707.signin.aws.amazon.com/console
Jatin.Patil@ril.com | _pUB#R1* | https://579654570707.signin.aws.amazon.com/console

## AI-ML Image
| Instance Type | No of Nodes
API server | m5.4xlarge | 2 | 16 vcpu 64GB RAM
Batch Processing Server (Image tagging and Face Finder) | m5.8xlarge | 2 | 32 vcpu 128GB RAM
DB Instance |  | 2 | 8vcpu 32GB RAM
S3 storage |  | 1
ELK |  |  | will be using of DEV Team

## DAMSTG
DAMDEV - AIML - SERVER LANDSCAPE
SR.NO. | SERVER IP PRIVATE | SERVER IP PUBLIC | INSTANCE NAME | SERVER MODEL | AMI - ARN | SERVER ROLE | AMI TYPE | VCPU | RAM (IN GB) | UID | running | Access key ID | Secret access key
1 | 172.40.19.205 | 18.177.142.12 | AIMLSTG-WB1VID | AWS EC2 |  | WEB | t2.xlarge | 4 | 16 | damweb |  | AKIAYN5Q22LJSRWDLW7K | #ERROR!
2 | 172.40.0.205 | 3.112.37.255 | AIMLSTG-WB2VID | AWS EC2 |  | WEB | t2.xlarge | 4 | 16 | damweb
3 | 172.40.226.104 |  | AIMLSTG-AP1APIVID | AWS EC2 |  | APP | t2.2xlarge | 8 | 32 | damapp
4 | 172.40.246.158 |  | AIMLSTG-AP1MTVID | AWS EC2 |  | APP | t2.2xlarge |  |  | damapp
5 | 172.40.238.101 |  | AIMLSTG-AP2APIIMG | AWS EC2 |  | APP | t2.2xlarge |  |  | damapp | API
6 | 172.40.176.147 |  | AIMLSTG-AP2MTIMG | AWS EC2 |  | APP | t2.2xlarge |  |  | damapp | scheduler
7 | 172.40.218.241 |  | AIMLSTG-AP2BPIMG | AWS EC2 |  | APP | t2.2xlarge |  |  | damapp | setup
8 | 172.40.214.93 |  | AIMLSTG-AP1BPVID | AWS EC2 |  | APP | t2.2xlarge |  |  | damapp
9 |  |  | aimlstginst | AWS RDS |  | DB | db.m6i.2xlarge | 16 | 64